# Enterprise Kubernetes Self-Service Platform - Implementation Project Plan

## Project Name: K8S Self-Service Platform
Version: 1.0
Date: 2026-01-21
Project Manager: Alex Lam, Bronson So

## 1. EXECUTIVE SUMMARY

### 1.1 Project Vision

To implement an enterprise-grade, secure Kubernetes self-service platform enabling teams/vendors to provision and manage their own containerized environments through GitOps workflows, while maintaining governance, security, and cost control.

### 1.2 Business Case

| Metric | Current State | Target State | Improvement |
| --- | --- | --- | --- |
| Time to provision environment | 3-5 days | 15 minutes | 99.3% faster |
| Admin overhead per request | 2-4 hours | 5 minutes | 96% reduction |
| Developer satisfaction score | 3.2/5 | 4.5/5 | 41% increase |
| Monthly infrastructure cost | $50,000 | $35,000 | 30% savings |
| Security compliance | Manual audits | Automated | 100% coverage |

### 1.3 Expected ROI

- Investment: $74,000 (Year 1)

- Annual Savings: $137,700

- ROI: 86.1% (Year 1)

- Payback Period: 6.4 months

- Intangible Benefits: Faster innovation, better security, talent retention

## 2. PROJECT ORGANIZATION STRUCTURE

### 2.1 RACI Matrix

| Role | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Project Sponsor |  | A | C | I |
| Project Manager (You) | R |  | C | I |
| Senior System Admin | R |  |  | I |
| System Admin Team | R |  |  | I |
| Security Division |  |  | C | I |
| Development Division Heads |  |  | C | I |
| IT Head |  |  |  | A |

### 2.2 Core Project Team

yaml

project_team:

project_manager:

name: "[Your Name]"

role: "Senior System Admin"

time_commitment: "100%"

platform_engineers:

- name: "[Colleague 1]"

role: "System Admin"

focus: "K8s Infrastructure, Networking"

- name: "[Colleague 2]"

role: "System Admin"

focus: "CI/CD, GitOps, Automation"

security_champion:

name: "[Security Team Rep]"

role: "Security Engineer"

time_commitment: "25%"

development_champion:

name: "[Lead Developer]"

role: "Senior Developer"

time_commitment: "15%"

## 3. PROJECT SCOPE

### 3.1 In Scope

✅ Phase 1: Foundation (Month 1-2)

- K8s cluster setup with industry-hardened configuration

- Core GitOps tooling (ArgoCD/Flux) implementation

- Base RBAC framework with NIST/ISO compliance

- Basic monitoring & logging stack

- Initial GitHub Actions CI/CD templates

- 1 pilot team onboarding

✅ Phase 2: Core Platform (Month 3-4)

- Self-service request workflow

- Automated approval system

- Cost monitoring & reporting

- Security scanning integration

- Multi-team RBAC expansion

- Vendor access framework

✅ Phase 3: Advanced Features (Month 5-6)

- Predictive scaling & optimization

- Executive dashboards

- Compliance automation

- Disaster recovery automation

- Advanced cost analytics

- Platform maturity metrics

### 3.2 Out of Scope

❌ Legacy application migration
❌ Custom application development
❌ 24/7 dedicated support team
❌ Performance tuning for specific applications
❌ Custom hardware procurement

## 4. TECHNICAL ARCHITECTURE

### 4.1 High-Level Architecture Diagram

text

┌─────────────────────────────────────────────────────────┐

│                    Developer Portal                      │

│        (GitHub/GitLab + Custom Request Forms)           │

└───────────────┬─────────────────────────────────────────┘

│

┌───────────────▼─────────────────────────────────────────┐

│                 CI/CD Orchestration                     │

│  GitHub Actions / GitLab CI / Jenkins / Tekton          │

└───────────────┬─────────────────────────────────────────┘

│

┌───────────────▼─────────────────────────────────────────┐

│                  GitOps Control Plane                   │

│          ArgoCD ApplicationSet + Helm + Kustomize       │

└───────────────┬─────────────────────────────────────────┘

│

┌───────────────▼─────────────────────────────────────────┐

│               Kubernetes Cluster(s)                     │

│  Production │ Staging │ Development │ Management        │

└───────────────┬─────────────────────────────────────────┘

│

┌───────────────▼─────────────────────────────────────────┐

│              Observability Stack                        │

│  Monitoring │ Logging │ Tracing │ Cost │ Security       │

└─────────────────────────────────────────────────────────┘

### 4.2 Technology Stack

#### Core Infrastructure

yaml

kubernetes:

distribution: "EKS/AKS/GKE or RKE2"  # Choose based on cloud

version: "1.28+"

network_plugin: "Calico/Cilium"

storage: "CSI with appropriate driver"

ingress: "NGINX/HAProxy/Traefik"

gitops:

operator: "ArgoCD"  # Recommended for enterprises

version: "2.9+"

sync_policy: "automated with pruning"

ci_cd:

primary: "GitHub Actions"  # Already mentioned

backup: "Tekton"  # For complex workflows

artifact_registry: "Harbor/ECR/ACR/GCR"

#### Security Stack

yaml

security:

policy_engine: "OPA/Gatekeeper"

secrets_management: "HashiCorp Vault + External Secrets Operator"

image_scanner: "Trivy/Clair/Aqua"

runtime_security: "Falco/Sysdig"

network_policy: "Calico Network Policies"

#### Monitoring Stack

yaml

monitoring:

metrics: "Prometheus + VictoriaMetrics"

visualization: "Grafana"

logging: "Loki + FluentBit"

tracing: "Jaeger/Tempo"

alerting: "AlertManager + PagerDuty/OpsGenie"

#### Cost Management

yaml

cost_management:

primary: "Kubecost"

backup: "OpenCost"

integration: "Cloud provider native tools"

reporting: "Custom dashboards + automated reports"

## 5. IMPLEMENTATION PLAN

### 5.1 Phase 1: Foundation Setup (Weeks 1-8)

#### Week 1-2: Environment Preparation

markdown

## Week 1 Tasks

- [ ] Project kickoff meeting with stakeholders

- [ ] Finalize infrastructure requirements document

- [ ] Set up project repositories (GitOps config, documentation)

- [ ] Create Terraform/IaC templates for K8s clusters

- [ ] Establish VPN/network connectivity requirements

## Week 2 Tasks

- [ ] Provision development Kubernetes cluster

- [ ] Configure base networking (CNI, Ingress, DNS)

- [ ] Set up storage classes and CSI drivers

- [ ] Deploy core monitoring stack (Prometheus, Grafana)

- [ ] Implement base backup strategy (Velero)

#### Week 3-4: Security Foundation

markdown

## Week 3 Tasks

- [ ] Implement Pod Security Standards (PSS)

- [ ] Deploy OPA/Gatekeeper with policies

- [ ] Set up HashiCorp Vault integration

- [ ] Configure image scanning pipeline

- [ ] Create base network policies

## Week 4 Tasks

- [ ] Implement RBAC framework

- [ ] Set up audit logging to SIEM

- [ ] Configure SSO integration (OIDC)

- [ ] Implement secret management workflow

- [ ] Security baseline documentation

#### Week 5-6: GitOps Foundation

markdown

## Week 5 Tasks

- [ ] Install and configure ArgoCD

- [ ] Create ApplicationSet templates

- [ ] Set up Helm repository

- [ ] Implement Kustomize overlays

- [ ] Configure sync waves and hooks

## Week 6 Tasks

- [ ] Create GitOps directory structure

- [ ] Implement promotion workflows (dev→staging→prod)

- [ ] Set up notification system (Slack/Teams/Email)

- [ ] Create rollback procedures

- [ ] Disaster recovery testing

#### Week 7-8: CI/CD Pipeline Foundation

markdown

## Week 7 Tasks

- [ ] Create GitHub Actions templates

- [ ] Implement build and test pipelines

- [ ] Set up artifact registry

- [ ] Configure deployment pipelines

- [ ] Create reusable workflow templates

## Week 8 Tasks

- [ ] Implement security scanning in pipelines

- [ ] Create cost estimation in PRs

- [ ] Set up quality gates

- [ ] Phase 1 documentation complete

- [ ] Phase 1 review with stakeholders

### 5.2 Phase 2: Self-Service Implementation (Weeks 9-16)

#### Week 9-10: Request Workflow

markdown

## Week 9 Tasks

- [ ] Design and implement request templates

- [ ] Create GitHub repository structure for requests

- [ ] Implement PR/MR automation

- [ ] Set up approval workflows

- [ ] Create automated validation checks

## Week 10 Tasks

- [ ] Implement environment provisioning automation

- [ ] Create namespace initialization templates

- [ ] Set up resource quota automation

- [ ] Implement network policy auto-generation

- [ ] Create access credential generation

#### Week 11-12: Multi-tenancy & RBAC

markdown

## Week 11 Tasks

- [ ] Implement team namespace structure

- [ ] Create team-specific RBAC roles

- [ ] Set up quota management per team

- [ ] Implement cost allocation tagging

- [ ] Create team onboarding documentation

## Week 12 Tasks

- [ ] Pilot with first development team

- [ ] Collect feedback and iterate

- [ ] Implement improvements based on feedback

- [ ] Create training materials

- [ ] Document operational procedures

#### Week 13-14: Monitoring & Observability

markdown

## Week 13 Tasks

- [ ] Implement application-level monitoring

- [ ] Create team-specific dashboards

- [ ] Set up automated alerts

- [ ] Implement log aggregation per team

- [ ] Create performance baseline metrics

## Week 14 Tasks

- [ ] Implement cost monitoring dashboards

- [ ] Set up anomaly detection

- [ ] Create capacity planning reports

- [ ] Implement SLA tracking

- [ ] Create operational runbooks

#### Week 15-16: Security & Compliance

markdown

## Week 15 Tasks

- [ ] Implement compliance scanning

- [ ] Create audit reports

- [ ] Set up security posture dashboard

- [ ] Implement vulnerability management

- [ ] Create incident response playbooks

## Week 16 Tasks

- [ ] Phase 2 rollout to 2 additional teams

- [ ] Security review and penetration testing

- [ ] Performance testing

- [ ] Phase 2 documentation complete

- [ ] Phase 2 review with stakeholders

### 5.3 Phase 3: Optimization & Scale (Weeks 17-24)

#### Week 17-18: Advanced Automation

markdown

## Week 17 Tasks

- [ ] Implement predictive autoscaling

- [ ] Create cost optimization recommendations

- [ ] Set up automated cleanup policies

- [ ] Implement just-in-time access

- [ ] Create self-healing mechanisms

## Week 18 Tasks

- [ ] Implement chaos engineering framework

- [ ] Create performance optimization tools

- [ ] Set up automated capacity planning

- [ ] Implement blue-green deployment automation

- [ ] Create canary release automation

#### Week 19-20: Governance & Reporting

markdown

## Week 19 Tasks

- [ ] Create executive dashboards

- [ ] Implement automated reporting

- [ ] Set up chargeback/showback system

- [ ] Create ROI tracking dashboard

- [ ] Implement business value metrics

## Week 20 Tasks

- [ ] Create compliance automation

- [ ] Implement policy as code

- [ ] Set up automated audits

- [ ] Create regulatory compliance reports

- [ ] Implement data residency controls

#### Week 21-22: Platform Maturity

markdown

## Week 21 Tasks

- [ ] Implement service catalog

- [ ] Create developer portal

- [ ] Set up internal marketplace

- [ ] Implement A/B testing framework

- [ ] Create feature flag management

## Week 22 Tasks

- [ ] Rollout to all development teams

- [ ] Create advanced training program

- [ ] Implement community of practice

- [ ] Create platform evangelism program

- [ ] Document best practices

#### Week 23-24: Handover & Sustainability

markdown

## Week 23 Tasks

- [ ] Create operational handover documentation

- [ ] Train operations team

- [ ] Implement on-call rotation

- [ ] Create maintenance schedules

- [ ] Set up continuous improvement process

## Week 24 Tasks

- [ ] Final security review

- [ ] Performance benchmark testing

- [ ] Project retrospective

- [ ] Success metrics reporting

- [ ] Project closure documentation

## 6. RISK MANAGEMENT PLAN

### 6.1 Risk Register

| Risk ID | Risk Description | Probability | Impact | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- | --- |
| RISK-001 | Kubernetes version compatibility issues | Medium | High | Test upgrades in staging, maintain rollback capability | You |
| RISK-002 | Security breaches through self-service | High | Critical | Implement OPA policies, regular security scans, RBAC reviews | Security Team |
| RISK-003 | Cost overruns from uncontrolled usage | High | High | Implement quotas, budget alerts, cost dashboards | You |
| RISK-004 | Developer resistance to new workflow | Medium | Medium | Early involvement, comprehensive training, pilot program | You |
| RISK-005 | Single point of failure in GitOps tooling | Low | High | Multi-cluster setup, backup procedures, disaster recovery | You |
| RISK-006 | Compliance violations | Medium | High | Automated compliance checks, audit trails, regular reviews | Security Team |
| RISK-007 | Performance degradation at scale | Low | Medium | Load testing, monitoring, autoscaling, capacity planning | You |
| RISK-008 | Vendor tool dependency | Low | Medium | Use open source where possible, maintain exit strategies | You |

### 6.2 Mitigation Actions

yaml

mitigation_actions:

security:

- "Weekly security scanning"

- "Monthly penetration testing"

- "Quarterly RBAC reviews"

- "Real-time anomaly detection"

cost_control:

- "Daily cost reports"

- "Weekly budget reviews"

- "Monthly optimization recommendations"

- "Quarterly financial review"

availability:

- "99.9% SLA for core services"

- "Multi-zone deployment"

- "Daily backups tested weekly"

- "Disaster recovery quarterly tests"

## 7. COMMUNICATION PLAN

### 7.1 Stakeholder Communication Matrix

| Stakeholder | Information Needs | Frequency | Format | Owner |
| --- | --- | --- | --- | --- |
| IT Head | Strategic updates, ROI, risks | Monthly | Executive summary + dashboard | You |
| Division Heads | Progress, team adoption, issues | Bi-weekly | Status report + metrics | You |
| Development Teams | How-to, changes, support | Weekly | Newsletter + office hours | You |
| Security Team | Security posture, incidents | Weekly | Security report | Security Champion |
| Project Team | Tasks, blockers, coordination | Daily | Standup + Slack | You |
| Finance | Cost reports, budget tracking | Monthly | Financial dashboard | You |

### 7.2 Communication Channels

yaml

communication_channels:

formal_reports:

- "Weekly status report (Confluence)"

- "Monthly executive dashboard (Grafana)"

- "Quarterly business review (PowerPoint)"

informal_updates:

- "Daily standup (Teams/Slack)"

- "Project channel (Slack #project-helios)"

- "Office hours (Weekly, open Q&A)"

documentation:

- "Technical docs (GitHub Wiki)"

- "User guides (ReadTheDocs)"

- "API documentation (Swagger)"

- "Runbooks (Confluence)"

## 8. QUALITY ASSURANCE PLAN

### 8.1 Testing Strategy

yaml

testing_strategy:

unit_tests:

- "Infrastructure as Code testing"

- "Policy validation testing"

- "Template validation"

- "Automation script testing"

integration_tests:

- "End-to-end workflow testing"

- "API integration testing"

- "Toolchain integration testing"

- "Security integration testing"

performance_tests:

- "Load testing (100+ concurrent requests)"

- "Scalability testing"

- "Stress testing"

- "Failover testing"

security_tests:

- "Penetration testing"

- "Vulnerability scanning"

- "Compliance validation"

- "Access control testing"

user_acceptance:

- "Pilot team testing"

- "Usability testing"

- "Documentation validation"

- "Training effectiveness"

### 8.2 Quality Gates

| Gate | Criteria | Exit Condition | Approver |
| --- | --- | --- | --- |
| Design Review | Architecture approved | Security & all stakeholders sign-off | Architecture Board |
| Security Review | All vulnerabilities addressed | Zero critical vulnerabilities | Security Officer |
| Performance Review | Meets SLA requirements | <2s response time, 99.9% availability | Division Head |
| User Acceptance | Pilot team satisfied | 90% satisfaction score | Pilot Team Lead |
| Production Readiness | All checks passed | Runbooks complete, team trained | You |

## 9. SUCCESS METRICS & KPIs

### 9.1 Technical KPIs

yaml

technical_kpis:

availability:

- "Cluster uptime: 99.9%"

- "GitOps sync success rate: >95%"

- "Pipeline success rate: >90%"

performance:

- "Environment provisioning time: <15 minutes"

- "API response time: <2 seconds"

- "Resource utilization: 60-80%"

quality:

- "Deployment failure rate: <5%"

- "Mean time to recovery: <1 hour"

- "Change success rate: >95%"

### 9.2 Business KPIs

yaml

business_kpis:

efficiency:

- "Admin time saved: >100 hours/month"

- "Developer wait time reduced: >90%"

- "Cost per environment: reduced by 30%"

adoption:

- "Team adoption rate: >80% within 6 months"

- "Active users: >50 developers"

- "Monthly environments created: >100"

satisfaction:

- "Developer satisfaction: >4.5/5"

- "Net Promoter Score: >50"

- "Support tickets reduced: >70%"

### 9.3 Financial KPIs

yaml

financial_kpis:

cost_savings:

- "Infrastructure cost reduction: 30%"

- "Operational cost reduction: 40%"

- "ROI: 86.1% Year 1"

value:

- "Features deployed per month: +300%"

- "Time to market: reduced by 80%"

- "Innovation projects enabled: +5/month"

## 10. BUDGET & RESOURCES

### 10.1 Budget Breakdown

| Category | Year 1 Cost | Year 2 Cost | Justification |
| --- | --- | --- | --- |
| Personnel (Your Team) | $45,000 | $47,250 | 3 months setup + ongoing maintenance |
| Kubernetes Infrastructure | $18,000 | $21,600 | Production + staging clusters |
| Tooling Licenses | $5,000 | $6,000 | Commercial tools (optional) |
| Training & Enablement | $3,000 | $1,500 | Team training, workshops |
| Contingency (15%) | $3,000 | $3,600 | Risk mitigation buffer |
| Total | $74,000 | $79,950 |  |

### 10.2 Resource Allocation

yaml

resource_allocation:

phase_1:

project_manager: "100% FTE"

system_admin_1: "50% FTE"

system_admin_2: "50% FTE"

security_champion: "25% FTE"

phase_2:

project_manager: "80% FTE"

system_admin_1: "30% FTE"

system_admin_2: "30% FTE"

security_champion: "15% FTE"

phase_3:

project_manager: "50% FTE"

system_admin_1: "20% FTE"

system_admin_2: "20% FTE"

security_champion: "10% FTE"

operational:

project_manager: "20% FTE"  # Ongoing platform ownership

system_admin_1: "10% FTE"   # On-call rotation

system_admin_2: "10% FTE"   # On-call rotation

## 11. DOCUMENTATION STRATEGY

### 11.1 Documentation Structure

text

docs/

├── project/

│   ├── charter.md

│   ├── roadmap.md

│   ├── risk-register.md

│   └── communications-plan.md

├── architecture/

│   ├── high-level-design.md

│   ├── technical-specifications.md

│   ├── data-flow-diagrams.md

│   └── decision-records/

├── operations/

│   ├── runbooks/

│   ├── procedures/

│   ├── incident-response/

│   └── disaster-recovery/

├── user-guides/

│   ├── getting-started.md

│   ├── tutorials/

│   ├── faq.md

│   └── best-practices.md

├── api/

│   ├── specifications/

│   ├── examples/

│   └── integration-guides/

└── compliance/

├── audit-trails/

├── security-policies/

├── compliance-reports/

└── regulatory-requirements/

### 11.2 Documentation Standards

- Living Documentation: All docs in Git, version controlled

- Automated Updates: CI/CD updates docs from code

- Review Process: Peer review for all technical docs

- Access Control: RBAC for documentation access

- Searchability: Centralized documentation portal

## 12. CHANGE MANAGEMENT

### 12.1 Change Control Process

### 12.2 Change Categories

| Change Type | Approval Required | Testing Required | Rollback Plan | Notification |
| --- | --- | --- | --- | --- |
| Emergency | Change Board (Expedited) | Minimal | Required | Immediate to affected |
| Standard | CAB Weekly | Full regression | Required | 48 hours notice |
| Minor | Team Lead | Unit tests only | Optional | Release notes |
| Documentation | Peer Review | N/A | N/A | N/A |

## 13. TRAINING & ENABLEMENT PLAN

### 13.1 Training Program

| Audience | Training Type | Duration | Deliverable | Success Metric |
| --- | --- | --- | --- | --- |
| System Admins | Platform Administration | 40 hours | Certified K8s Admin | 100% certification |
| Developers | Self-Service Usage | 8 hours | Hands-on workshop | 90% satisfaction |
| Team Leads | Governance & Approval | 4 hours | Workshop + guide | 100% attendance |
| Security Team | Security Monitoring | 8 hours | Security runbooks | All runbooks tested |
| Managers | Dashboard Usage | 2 hours | Executive briefing | Monthly dashboard usage |

### 13.2 Enablement Materials

- Video Tutorials: Short (<5 min) focused videos

- Interactive Labs: Hands-on sandbox environments

- Cheat Sheets: One-page reference guides

- Office Hours: Weekly Q&A sessions

- Community Forum: Internal discussion board

## 14. SUSTAINABILITY & OPERATIONS

### 14.1 Operational Model

yaml

operations_model:

support_tiers:

tier_1:

name: "Platform Support"

response_time: "4 business hours"

scope: "Usage questions, basic troubleshooting"

tier_2:

name: "Technical Support"

response_time: "2 business hours"

scope: "Technical issues, configuration"

tier_3:

name: "Platform Engineering"

response_time: "1 business hour"

scope: "Platform bugs, emergencies"

maintenance_windows:

regular: "Sunday 02:00-04:00 (weekly)"

critical: "As needed with 48h notice"

emergency: "Immediate with notification"

on_call_rotation:

primary: "You"

secondary: "System Admin 1"

tertiary: "System Admin 2"

escalation: "Division Head"

### 14.2 Continuous Improvement

yaml

improvement_process:

feedback_loops:

- "Monthly user feedback sessions"

- "Quarterly platform review"

- "Annual strategic planning"

metrics_review:

- "Weekly KPI review"

- "Monthly operational review"

- "Quarterly business review"

innovation_time:

- "10% time for platform improvements"

- "Quarterly hackathons"

- "Annual platform summit"

## 15. PROJECT CLOSURE CRITERIA

### 15.1 Success Criteria

- All technical components deployed and operational

- Success metrics achieved or exceeded

- All documentation complete and reviewed

- Training completed for all user groups

- Operational handover complete

- Stakeholder sign-off obtained

- Post-implementation review conducted

- Lessons learned documented

- Sustainability plan in place

### 15.2 Project Closure Checklist

markdown

## Administrative Closure

- [ ] All financial transactions closed

- [ ] Contracts and licenses documented

- [ ] Resource reallocation completed

- [ ] Project archive created

## Technical Closure

- [ ] Code repositories handed over

- [ ] Access rights reviewed and updated

- [ ] Monitoring and alerting operational

- [ ] Backup and recovery tested

## Knowledge Transfer

- [ ] Runbooks handed to operations team

- [ ] Training materials delivered

- [ ] Key contacts documented

- [ ] Community of practice established

## 16. APPENDICES

### 16.1 Glossary of Terms

| Term | Definition |
| --- | --- |
| GitOps | Operational framework using Git as single source of truth |
| RBAC | Role-Based Access Control |
| CI/CD | Continuous Integration/Continuous Deployment |
| IaC | Infrastructure as Code |
| SLA | Service Level Agreement |
| KPI | Key Performance Indicator |
| ROI | Return on Investment |
| OPA | Open Policy Agent |

### 16.2 Reference Architecture Diagrams

(Attach Visio/Lucidchart diagrams)

### 16.3 Compliance Requirements

(List specific compliance standards: ISO 27001, SOC2, HIPAA, etc.)

### 16.4 Tool Evaluation Matrix

(Comparison of evaluated tools with selection rationale)

## SIGNATURES

Project Sponsor (Infrastructure Division Head):

- Name: _________________________

- Signature: _____________________

- Date: _________________________

Project Manager (You):

- Name: _________________________

- Signature: _____________________

- Date: _________________________

IT Head:

- Name: _________________________

- Signature: _____________________

- Date: _________________________